Foot Locker AI Development Learning Program

450-FTE Cohort Enablement  |  Waves in Series  |  Embedded Engineers

PREPARED BY

Improving

June 2026  |  DRAFT

Executive Summary

Foot Locker is preparing to activate enterprise-wide AI licensing across its global technology organization and is building the enablement strategy to go with it. The central challenge is not tooling — it is adoption. Industry data puts only 13% of knowledge workers using AI daily, and training-only approaches consistently plateau after rollout, peaking at 45% adoption before receding to single digits. The programs that work are applied, team-based, and grounded in real sprint work.

This proposal outlines a Development Learning Program (DLP) for approximately 450 FTE developers delivered in series: a validated MVP followed by two full waves, each covering 10 cohorts across 12 weeks. Every cohort operates under hard team size limits, with a dedicated embedded engineer per team and an enterprise coach who plans and anchors each wave. The result is compounding productivity gain — observed at 5-15% by end of week 12 and 20-30% at the six-month mark — with governance infrastructure that compounds across all three phases under full Improving leadership.

At 450 FTE developers with an average fully loaded cost of $165K/person, the program pays for itself at approximately a 9.8% sustained productivity improvement — call it 10%. The DLP model at 1 EE per team produces 11-18% in-program; 20-30% at six months post-program.

Program Architecture

Design Principles

Applied over classroom. Every cohort combines bi-weekly workshops with sprint-embedded coaching. Developers build real agents against their real work, not synthetic exercises.

In series, not all at once. Waves run sequentially to control quality, allow governance to mature, and let embedded engineer patterns compound before scaling.

Hard team size limits. No team exceeds 8 people; no cohort exceeds 24. One embedded engineer per team, not shared. This protects coaching quality at scale.

Tech-stack-aligned cohorts. Teams within a cohort share languages and tools (e.g., C#/.NET, Java, React/Node.js). Embedded engineers are not context-switching mid-wave.

Enterprise coach as planner and anchor. Starts 4 weeks before each wave to design cohort composition, wave sequencing, and governance structure. Drives OCM for identity-based resistance.

Improving-led through all three phases. Wave 2 uses the same Improving-staffed embedded engineer model as Wave 1. Full program management does not transfer until after program completion.

Phase Structure

The program runs in three sequential phases. Total duration is approximately 48-52 weeks end-to-end, inclusive of planning periods.

| Phase | Cohorts | People | Teams | Emb. EEs | Duration | Improving Role |
| --- | --- | --- | --- | --- | --- | --- |
| MVP (Phase 0) | 1 | 8-16 | 1-2 | 1-2 | 16 wks (4 plan + 12 exec) | Full lead |
| Wave 1 | 10 | ~240 | ~30 | ~30 | 16 wks (4 plan + 12 exec) | Full lead |
| Wave 2 | 8-9 | ~195 | ~24 | ~24 | 16 wks (4 plan + 12 exec) | Full lead |
| Total Program | ~19-21 | ~450 | ~54-60 | — | ~48 weeks | Improving-led |

Hard Team Size Limits

These limits are structural, not advisory. They protect coaching quality and prevent the most common failure mode — licensing without guidance.

| Constraint | Hard Limit |
| --- | --- |
| People per team | Max 8 |
| Teams per cohort | Max 3 (tech-stack aligned) |
| People per cohort | Max 24 |
| Embedded engineers per team | 1 (dedicated, not shared) |
| Cohorts per wave | 10-12 (trainer scalable) |
| Waves in parallel | 0 (series model) |

Program Components

Enterprise Coach

The enterprise coach is the program anchor. Engagement starts four weeks before the first cohort's day one in each wave and runs full-time through the entire 16-week wave. Primary responsibilities:

Designs cohort composition: maps teams to cohorts by tech stack and business priority

Sequences waves against delivery commitments to avoid endangering critical programs

Drives OCM: addresses identity-based resistance (senior developers are the highest long-term multipliers but slowest early adopters)

Establishes governance infrastructure: skills repository structure, agent promotion process, cost-to-capacity dashboards

Coaches individuals flagged by governance signals (over-reliance, under-adoption, high spend with no outputs)

Manages passive-to-active compliance transition (e.g., PCI-active agents in the SDLC)

Tracks governance maturity across all active cohorts; escalates quality issues to embedded engineers and program leadership

The enterprise coach is full-time throughout each wave — both during the 4-week planning period and the 12-week execution period. This role remains Improving-managed across all three phases of the program.

Embedded Engineers

One embedded engineer per team. They do not rotate between teams while a wave is active. This is not a shared resource model — each engineer is dedicated to 8 people for the full 12 weeks.

Present during sprint work, not just workshops

Provide on-the-job coaching: context management, task decomposition, agent development, evaluation scoring

Introduce starter agents and help teams refine them against measurable outputs (bugs, test failures, cycle time)

Participate in bi-weekly agent review with the enterprise coach to identify candidates for promotion to the shared repository

Hand off improvement documentation to the team at wave close so the cycle continues without them

For a 10-cohort wave with an average of 3 teams per cohort, this requires approximately 30 embedded engineers. Foot Locker's remote-first engineering model means most embedded work is virtual, with optional hub coordination in the Plano (Dallas metro) area.

Trainer

Training is delivered as a half-day workshop every two weeks — six sessions over the 12-week program. Trainers scale efficiently: one trainer supports up to 10 cohorts per wave. Two trainers cover a full wave.

Workshop curriculum alternates through three phases, each repeated twice:

Define: structured prompting framework, task breakdown, context aggregation

Build: task agents, workflow agents, evaluation-driven prompt and agent development

Verify: CI/CD integration, agent quality scoring, governance and compliance agents

A key principle: model strength selection is based on clarity of intent, not problem complexity. Teams that internalize this see cost-to-capacity ratios improve within the first wave.

12-Week DLP Curriculum

The program builds Stage 3 and Stage 4 capability on Improving's eight-stage AI maturity model — moving teams from ad hoc usage to evaluated, reusable task agents and composed workflow agents.

| Weeks | Phase | Curriculum Focus | Embedded Engineer Activity |
| --- | --- | --- | --- |
| 1-2 | Define | Prompting framework, task decomposition, context aggregation, model selection principles | Establish team baseline; introduce starter agents by language/stack |
| 3-4 | Define | Structuring intent across the team value stream (product to dev to test) | Coach intent specification in sprint work; identify first evaluation targets |
| 5-6 | Build | Task agent construction, evaluation-driven development, prompt scoring methodology | Build and score first team agents against sprint outputs (bugs, failures) |
| 7-8 | Build | Workflow agents, harness selection, composed agent patterns | Identify repeatable workflows; draft first workflow agents with the team |
| 9-10 | Verify | CI/CD agent integration, automated testing agents, verification debt reduction | Wire agents into CI pipeline; instrument acceptance rate and reliance signals |
| 11-12 | Verify | Agent promotion process, skills repository, governance handoff, continuous improvement loop | Candidate agents for shared repository; document improvement roadmap for handoff |

MVP Recommendation

Before committing to a full wave, Improving recommends a single-cohort MVP: 1-2 teams (8-16 people) through the full 12-week DLP. The MVP is not a watered-down version — it uses the same embedded engineers, same enterprise coach setup, same workshop cadence, and produces the same governance outputs. It is the proving ground for Foot Locker's specific context before scaling.

Suggested MVP team selection criteria:

A team with a defined upcoming sprint cycle (not mid-project)

Tech stack that will represent the largest cohort group in Wave 1 (likely C#/.NET or Java given Foot Locker's confirmed primary stacks)

A team lead willing to champion the model and engage actively with the embedded engineer

Manageable DevOps maturity — not the weakest team, not the strongest

MVP success metrics to align on before kickoff:

Velocity change (sprint story points or cycle time, measured week 1 vs. week 12)

AI acceptance rate (target: approximately 85-90%, flagging over-reliance and under-reliance)

Agent quality scores (bug rate, test failure rate compared to pre-program baseline)

Team-reported confidence index (subjective, tracked at weeks 4, 8, and 12)

Improving ran a comparable single-team pilot for Insperity (an HR/PEO company) before scaling to 50 teams. The same model — one team, full program, full governance — validated the approach and produced the executive ROI narrative that unlocked the broader engagement.

DevOps Acceleration Track (Optional)

Foot Locker's current DevOps maturity is a limiting factor for AI-enabled development. Teams without robust CI/CD, automated testing, and infrastructure-as-code carry verification debt — AI generates output faster than humans can verify it. This is the most common bottleneck in organizations with sub-mature SDLC practices, and it caps the productivity gain achievable through the DLP alone.

This track is optional. Teams with mature CI/CD and automated testing can proceed directly to the DLP and will not be blocked. This track is recommended for any team that lacks baseline pipeline automation before entering Wave 1.

DevOps Specialist Team

Improving provides two dedicated DevOps Specialists embedded alongside the DLP for 12-24 weeks. These are not trainers — they are practitioners building the pipeline infrastructure that lets AI productivity gains actually ship.

| Role | Duration | Deliverables |
| --- | --- | --- |
| DevOps Specialist 1 (Pipeline & CI/CD) | 12-24 weeks | CI/CD pipeline deployment per team; automated testing framework (unit, integration, regression); PR gates and protected branch configuration; merge automation guardrails with mandatory human review thresholds |
| DevOps Specialist 2 (Observability & IaC) | 12-24 weeks | Infrastructure-as-code for deployment environments; AI acceptance rate and code quality instrumentation; governance signal feeds into Power BI dashboards; token guardrail alerts; agent CI/CD integration |

What the DevOps Team Builds

CI/CD pipelines: automated build, test, and deploy pipelines for DLP cohort teams using AI-assisted Terraform. Teams leaving the DLP without this infrastructure cannot sustain their productivity gains.

Automated testing framework: unit, integration, and regression test suites configured before Wave 1 cohorts go live. This is the verification layer that makes AI acceptance rates meaningful.

AI acceptance rate instrumentation: tooling that surfaces per-developer and per-team acceptance rates, reliance signals, and spend-to-output ratios into governance dashboards.

Agent CI/CD integration: tested prompts and agents promoted through the agent repository are automatically evaluated on deploy; performance regressions fail the pipeline before they reach teams.

Token cost guardrails: configures alerts and spending controls for GitHub Copilot, Claude, and Microsoft Copilot.

Engagement Phasing

| Weeks | Phase | Activity |
| --- | --- | --- |
| 1-4 | Assessment | Current-state CI/CD audit per team; testing coverage baseline; IaC gap analysis; prioritized build list for Wave 1 readiness |
| 5-12 | Build (Wave 1 Prep) | CI/CD pipelines deployed for Wave 1 cohort teams; automated testing frameworks live; acceptance rate instrumentation active before first cohort day one |
| 13-20 | Extend (Wave 1 Run) | Remaining teams onboarded; agent CI/CD integration; token guardrails and cost monitoring live; governance signal feeds into dashboards |
| 21-24 | Handoff (Optional) | IaC templates and runbooks transferred to Foot Locker platform team; pipeline templates published to internal repository; Improving in advisory role only |

Data & Compliance Enablement Team

Foot Locker operates under PCI DSS, SOX, and GDPR. As AI is introduced into the SDLC, passive compliance — end-of-cycle audits — does not catch AI-generated code that introduces scope creep, credential mishandling, or audit trail gaps. The Data & Compliance team makes compliance active and continuous across all three frameworks.

Team Composition

Improving provides two dedicated BI/Data engineers for 16 weeks, embedded alongside the program's governance framework build-out. These are practitioners building the infrastructure that makes AI adoption safe at Foot Locker's scale.

| Role | Duration | Deliverables |
| --- | --- | --- |
| BI/Data Engineer 1 (Governance) | 16 weeks | PCI-active and SOX-aware agent framework; compliance signal dashboards on Fabric/Power BI; agent acceptance and reliance tracking; spend-to-output monitoring; agent promotion governance process |
| BI/Data Engineer 2 (Data Compliance) | 16 weeks | PCI + SOX scope boundary mapping; data classification agent integration; zero-retention policy enforcement tooling; SOX-traceable audit artifact generation for AI-assisted PRs; GDPR data residency controls |

What the Data & Compliance Team Builds

PCI-active agent in the SDLC: runs on every commit touching PCI-scope code, flags issues inline rather than at audit time. Prevents AI-generated code from silently introducing out-of-scope data handling.

SOX audit trail generation: every AI-assisted code change carries a traceable attribution record. AI-generated contributions are tagged at the commit level to satisfy SOX change management controls and support auditor review.

Data classification layer: classifies data across AI tool call chains (Copilot, Claude, GitHub Copilot) to ensure PII, cardholder data, and SOX-sensitive systems data is never passed to models without proper controls.

Governance dashboards (Fabric/Power BI): real-time visibility into adoption signal, spend, acceptance rates, and code quality indicators across all active teams and cohorts.

Audit-ready artifact generation: automatically produces evidence records for AI-assisted PRs. Designed to satisfy PCI DSS Req. 6.x and SOX IT General Controls for software development practices.

Agent policy infrastructure: enforces rules on which tools can access which data environments, zero-retention configurations for PCI-scope workflows, permission scoping per team.

The governance infrastructure should be operational before Wave 1 cohorts go live — not built after the fact. The 16-week engagement overlaps with the MVP and Wave 1 planning period by design.

Phased Compliance Build

| Weeks | Phase | Activity |
| --- | --- | --- |
| 1-4 | Discovery | PCI scope boundary mapping; data classification audit; AI tool call chain analysis; governance dashboard requirements |
| 5-8 | Build | PCI-active agent build and testing; data classification layer deployment; initial governance dashboards live |
| 9-12 | Integrate | Agent integration with Wave 1 CI/CD pipelines; audit artifact templates deployed; acceptance/reliance tracking live |
| 13-16 | Operationalize | Handoff to Foot Locker data/governance team; runbooks, alert configurations, policy documentation; compliance infrastructure fully transferred |

Governance Framework

Why Governance Is Not Optional

AI governance is not an afterthought in this program — it is the mechanism that makes scaling safe. Without it, Foot Locker faces three concrete risks:

Cost escalation: developers running expensive models on tasks that smaller models handle adequately. We have seen organizations spend 3-4x the necessary token cost in the first 90 days.

Cognitive surrender: developers accepting 100% of AI-generated code. The current observed accuracy rate for AI code generation is approximately 87%, meaning a 100% acceptance rate is introducing roughly 13% slop into the codebase.

Compliance exposure: Foot Locker operates under PCI, SOX, and GDPR. Passive compliance checks do not catch issues introduced by AI-generated code. Active compliance agents running on every commit do.

Governance Components

Multi-tool spend dashboard (GitHub Copilot, Claude, Microsoft Copilot): monitors daily spend per user, weekend usage anomalies, spend-to-output ratios

Adoption-to-operate signal tracking: distinguishes teams in the adoption stage (drive usage) from teams in the operate stage (drive output quality)

Acceptance rate and reliance rate monitoring: flags over-reliance (>90% acceptance) and under-reliance (<60% acceptance) as coaching triggers, not punitive measures

PCI and SOX compliance agents in SDLC: run on every commit for compliance-scope code, flag and surface issues inline rather than at audit time; SOX changes carry traceable attribution for IT General Controls

Agent promotion board: bi-weekly review with enterprise coach and EEs to evaluate team-built agents for promotion to the shared Foot Locker repository

Skills repository structure: globally true agents (compliance, security, SOX/PCI audit), domain-specific agents (C#/.NET, Java, React/Node.js), and business-specific agents (Foot Locker brand and commerce systems)

Improving will provide governance templates built on Fabric and Power BI as a starting point, adapted from infrastructure used internally and with NRG, Siemens, and ABB.

Value Realization

Most AI programs cost a lot of money and never reach breakeven. The MIT, McKinsey, and University of Chicago research all find that fewer than 20% of enterprise AI programs generate positive returns. The programs that fail share a pattern: wide tooling deployment, minimal behavior change, and no measurement infrastructure. The programs that succeed are measured, coached, and applied to real work.

The program investment is $7,280,700. The right frame for that number is a single question: what sustained productivity improvement across the 450-FTE developer organization is needed to recover the full investment in Year 1? The answer is 9.8% — call it 10%. Every scenario below sits above or below that threshold. The primary value lever is capacity recovery: teams complete more work in the same time, without headcount changes.

Baseline Assumptions

Developer population in scope: 450 FTE

Estimated fully loaded cost per developer (salary + benefits): $165,000 / year

Total annual developer investment: ~$74.3M

Productivity measurement: features shipped to production at sufficient quality — not lines of code, not hours logged

Baseline period: the 12 months prior to program start

Measuring AI productivity in lines of code is a trap. A model can generate 10,000 lines of low-quality code that creates more rework than it saves. The relevant measure is features shipped to production at quality — sprint output that actually ships, without regressions.

FTE Capacity Recovery Model

At a given productivity lift, developers complete the same volume of work in less time — the freed capacity is directed elsewhere without adding headcount.

| Scenario | Productivity Lift | Effective FTEs Recovered | Annualized Value | Payback on Investment |
| --- | --- | --- | --- | --- |
| Breakeven | ~10% | ~45 FTEs | ~$7.4M | ~12 months |
| Conservative (sub-breakeven) | 5% | ~23 FTEs | ~$3.7M | ~24 months |
| In-program (1 EE/team) | 11-18% | ~50-81 FTEs | $8.2-13.4M | 7-11 months |
| Post-program (6-12 months) | 20-30% | ~90-135 FTEs | $14.9-22.3M | 4-6 months |

Improving has completed more than a dozen DLPs. Observed productivity outcomes vary directly with the embedded engineer ratio. At First United Bank (Dallas), one embedded engineer coaches 24 developers across three teams — a budget-constrained 1:24 configuration. That ratio consistently yields 3-7% velocity improvement by program end. The EWN engagement (Dallas, Microsoft stack, Claude subscriptions) tracks the same pattern. The Foot Locker model proposes one embedded engineer per team — a 1:8 configuration — which is the ratio that produces 11-18% in-program velocity improvement in engagements where it is maintained. Post-program, teams that continue building on the agent patterns and established habits reach 20-30% productivity gain at the 6-12 month mark.

At the proposed 1-EE-per-team structure, Improving DLP engagements observe 11-18% velocity improvement during the active 12-week program — above the 9.8% breakeven threshold. At 6-12 months post-program, teams compound on agent patterns and reach 20-30% productivity gain. The investment pays back within the program period at the expected lift range. Post-program compounding is upside, not the thesis.

What Drives Adoption (and What Kills It)

The failure mode is almost always people, not tools. Specifically:

Senior developers are the highest long-term multipliers. They are also the slowest early adopters. They have spent years developing craft, and AI feels like it cheapens it. Getting them to change behavior requires a different conversation than the one that works for junior developers.

If leadership is not visibly using and endorsing the tools, adoption craters after the training ends. Programs that do not activate sponsors at the exec level end up at under 20% daily usage.

Acceptance rate signals are early indicators. An 87% acceptance rate means the developer is reviewing and editing AI output appropriately. 99%+ means cognitive surrender. Both extremes require coaching, not technology fixes.

This is why the enterprise coach exists and why the embedded engineers stay for the full 12 weeks. Classroom training changes knowledge; presence in the sprint changes behavior.

Productivity Lift Scenarios

| Scenario | Productivity Lift | Annual Gain | 3-Year Cumulative | 3-Year Multiple on $7.28M |
| --- | --- | --- | --- | --- |
| Breakeven | ~10% | ~$7.4M | ~$22.3M | 3.1x |
| In-program, DLP model (1 EE/team) | 11-18% | $8.2-13.4M | $24.5-40.1M | 3.4-5.5x |
| Post-program compounding (6-12 mo) | 20-30% | $14.9-22.3M | $44.6-66.8M | 6.1-9.2x |
| Full program, 70% adoption, 12 months | 30% | $22.3M | $66.8M | 9.2x |

These are capacity recovery scenarios — not headcount reduction. Foot Locker's stated goal is to build more, ship faster, and carry less maintenance burden with the same team.

Timeline to Value

| Milestone | Expected Outcome |
| --- | --- |
| Week 12 (end of MVP) | First team at 5-15% velocity improvement; governance baseline established; executive ROI narrative with Foot Locker-specific data |
| Week 24 (Wave 1 mid) | ~120 developers active; governance dashboards live; PCI and SOX compliance agents in CI pipeline; early adoption signals available |
| Week 28 (end of Wave 1) | ~240 developers through program; 30 embedded engineers available as internal trainers; skills repository populated; go/no-go for Wave 2 |
| Week 44 (end of Wave 2) | ~450 FTE developers through program; Improving-led completion; full governance and compliance infrastructure operational; agent repository active across all teams |
| Month 12 | Full developer population at 12%+ productivity lift; governance dashboard active; agent repository in use across all Foot Locker teams |

Investment Summary

$7,280,700 total program investment. At 450 FTE developers and $74.3M annual developer payroll, the program requires approximately 9.8% sustained productivity improvement to recover the full investment in Year 1. The DLP model — one embedded engineer per team — targets 11-18% velocity improvement during the active 12-week program, with 20-30% at 6-12 months post-program.

| Phase | Scope | Investment |
| --- | --- | --- |
| MVP | 2 teams (~16 developers) | $375,100 |
| Wave 1 | 10 cohorts (~240 developers) | $3,328,000 |
| Wave 2 | ~195 developers — Improving-managed | $3,328,000 |
| Data / Compliance Track | 2 engineers × 16 weeks | $249,600 |
| Total Program | ~450 FTE developers | $7,280,700 |

Pricing Options

Two structures are available depending on Foot Locker's preferred engagement model:

All-in program price: Single $7,280,700 investment covers all three phases. Simplest to approve; provides Improving's best total pricing.

Phase-gated pricing: MVP ($375,100) priced independently as a proof-of-value entry point. Subsequent waves priced separately, contingent on MVP outcomes. Higher per-cohort cost but lower initial commitment.

Why Improving

Improving has trained and upskilled over 60,000 developers and knowledge workers in applied AI programs. The DLP is the same program Improving runs internally — Tim Rayburn's team has put 1,400 Improving developers through it in the past six months. We do not sell a training product we have not built our own practice on.

| Engagement | Scale | Outcome |
| --- | --- | --- |
| NRG (Energy) | 1,600 developers | AI DLP across all SDLC roles; 4 waves in 11 months; train-the-trainer transfer |
| Alberta Blue Cross | 450+ SDLC roles (regulated) | Phase 0-3 DLP with governance; 40% adoption = 8-11 FTE recovered; 12-16 month payback; PCI/COBIT compliance embedded |
| Verizon | 61,000 employees | Ongoing enablement at enterprise scale |
| Improving (internal) | 1,400 developers | 6 months; own team as reference; full governance infrastructure |
| Mid-size regional bank (Dallas) | ~200 developers | Started 1 team; scaled to multiple cohorts; ongoing |

Improving is not a large-MSP competitor. Foot Locker will not be one of dozens of accounts where the program is executed by a contractor who read the playbook last week. The people who designed these programs are the same people who will be in your sprints.

Proposed Next Steps

| # | Action | Owner / Timing |
| --- | --- | --- |
| 1 | Review this proposal with Ross and Patrick; align on MVP team selection criteria | Diana + Ross Clanton ¦ Within 1 week |
| 2 | Foot Locker provides tech stack breakdown and team org structure for Wave 1 cohort planning | Patrick + Foot Locker IT ¦ Within 2 weeks |
| 3 | Finalize MVP scope: 1-2 teams, start date, success metrics, governance baseline | Improving + Foot Locker ¦ Within 2 weeks |
| 4 | Commercial proposal review (separate call before distribution) | Diana + account lead ¦ Before broad send |
| 5 | Send follow-up materials: DLP deck, governance dashboard examples, model targeting guide | Improving ¦ This week |
| 6 | Optional: introduce Ross Clanton to a current DLP customer (Dallas) for peer reference | Improving ¦ Per Ross's interest |

Terminology Reference

| Term | Definition |
| --- | --- |
| Track | The full series of 6 bi-weekly workshops delivered to a single cohort over 12 weeks. Cost unit for trainer delivery. |
| Cohort | One group of up to 24 participants (max 3 teams) who go through the DLP together. Aligned by tech stack. |
| Team | The base unit: max 8 people per team. Receives one dedicated embedded engineer for the wave duration. |
| Embedded Engineer (EE) | An Improving engineer dedicated to one team for the full 12 weeks. Coaches in sprint work; not shared across teams. |
| Enterprise Coach | Senior program manager who starts 4 weeks pre-wave and remains full-time throughout. Plans cohort composition, drives OCM, owns governance framework. |
| Wave | One full program execution: 10-12 cohorts running the 12-week DLP simultaneously, preceded by a 4-week planning period. |
| Agent Repository | Shared library of promoted agents — task agents and workflow agents — accessible to all Foot Locker teams after Wave 1. Populated by embedded engineers and governed by the enterprise coach. |
| DLP | Development Learning Program. Improving's 12-week applied AI enablement program for software development teams. |